## Master - Backlog
Enhancement List
Num | Functionality | Type of Change | Description | Priority | Time | Status | Action | Notes
6 | Instruction Allocation | New Addition | Only allocate to users who have that instruction allocation | High | 1 | Done |  | In production in Zambia
8 | Instruction Allocation | New Addition | Return to sender not user type | High | 1 | Done |  | In production in Zambia
17 | Instruction Management | New Addition | Ability to resend a return instruction from IBC | High | 1 | Done |  | In production in Zambia
1 | File Upload | New Addition | Excel File Upload and Download | High | 1 | Done |  | In UAT in Zambia
7 | Instruction Allocation | New Addition | Don't allow users to be unassigned instruction type (default allocation) | High | 1 | Done |  | In UAT in Zambia
24 | Email Notifications | New Addition | Email notification when an instruction has been returned back to a user | High | 1 | Done |  | In production in Zambia
3 | Reporting | New Addition | View all reports and be able to export | High | 1 | In Progress | Need to find out what users want from reports | Wait on response from Clara about what she wants
12 | Instruction Management | New Addition | Cut off time | High | 1 | Done | Admin can set cutoff time for any transaction. | In UAT in Zambia
2 | File Upload | New Addition | Multiple PDFs upload | Low | 3 | Not Allocated for Dev
4 | Email Notifications | New Addition | Email Escalation | High | 1 | Not Allocated for Dev |  | RMs >> Returned back to branch - send mail to owner and client access group ref 23
5 | Email Notifications | New Addition | Auto send email for past due instruction | High | 2 | Not Allocated for Dev
29 | Configurability | New Addition | Remove the need for configuration changes in CIMS to be made using SQL. Admins should be able to change everything they need to from the front end. | High | 3 | Done |  | Add admin panel functionality: make instruction types active, change instruction names, delete users, edit user logins.
13 | Reporting | New Addition | Option to select more than one filtering option from the dropdowns i.e. tick box to choose the instruction type they prefer to view | Low | 1 | Done |  | In production in Zambia
28 | Instruction Management | Change | Change the table columns that are displayed and allow filtering by instruction status | Low | 1 | In Progress
9 | Instruction Creation | New Addition | Auto generate reference | Low | 1 | Not Allocated for Dev
10 | User Profile | New Addition | Dual User Types - Ability for a user to have different profile roles/rights (i.e. can originate and validate an instruction) | Low | 1 | Not Allocated for Dev |  | Ref SN: 10. This was requested from Tanzania and Zambia. Possibility of CCC users to have all the three profile rights .i.e. Originator, Call-back and PRMO. But the user one user should not be able to perform a task end to end. E.g. originate, perform call-back and DD. This is for purpose of backup and the team has few staff but involved in multiple activities
11 | User Profile | New Addition | AD Password | Low | 2 | Not Allocated for Dev
20 | User Setup | New Addition | Possibility of three users with different profiles. i.e. Payment Originator for CIB, Call-back officer for CIB and PRMO for CIB to have one Team leader this is in particular for teams with teams with few people but their unit is involved in more than one activity | Low | 3 | Not Allocated for Dev |  | Ref SN: 9
22 | Workflow Configuration | Change | Priority adjustment of instruction. Payments which were returned to branches a day before should always come at the top of the queue when the same is returned to processing team | Low | 3 | Not Allocated for Dev |  | Ref SN: 12
23 | Email Notifications | Change | Disable all email alert to RMs/Transaction Bankers during normal activities. They currently receive emails for every activity happening on an instruction. RMs should receive emails only when an instruction is returned for a specified reason | Medium | 2 | Not Allocated for Dev |  | Ref SN:13
16 | Reporting | New Addition | To have EOD reports for processing teams which will have a column to show all branches since they will receive payments from all branches but the originator should be able to only see for their branch. OTT/RTGS should be separated from Vouchers/Salaries since they are processed with different teams | Medium | 1 | Not Allocated for Dev |  | NB Branch filtering
18 | Instruction Management | New Addition | Ability to change the instruction type when the incorrect one was selected | Medium | 2 | Not Allocated for Dev |  | Ref SN:7 : Originator to be able to edit instruction type when payment is return to them but the reference to indicate Modified and the same be tracked in audit trail. Currently they only delete and reload another instruction due to this restriction.
21 | Workflow Configuration | Change | All salaries should have an option submit to PRMO option currently PBB goes to PRMO while CIB goes to Payments team who in turn will have to forward to PRMO. This causes delays in processing | Medium | 1 | Not Allocated for Dev |  | Ref SN:11
22 | Instruction Management | New Addition | Standing Settlement Instruction. When a customer would process the same OTT every week or month, save the instruction in CIMS and automatically generate a new instance of it each time it was meant to re-occur | Medium | 2 | Not Allocated for Dev
27 | Botswana Update | Update
28 | PBB Account Opening
Total Backlog Items |  | 26
Status | Not Allocated to Dev | 13
| In Progress | 2
| Done | 9

## Tanzania
TANZANIA CIMS Issue Tracker
Sr | Date | User Profile | Issue Identified | Dennis Comments | Country Comment | Priority
1 | 03.09.2015 | All | Various reports -- List of reports shared |  | Regarding the report i.e. additional and existing once users requested to have the following • Option to have multiple selection i.e. tick box to choose the instruction type they prefer to check. • Extraction in excel or even option of printing in pdf. These options can be in reports like Daily Processed, Detailed Transaction Log and Unprocessed report per user. | High
2 | 04.09.2015 | Parked queues | Possibility of populating new comment for packing reasons when discovered that the comments populate earlier were not correct while keeping the audit trail of what was populated before. |  |  | Low
3 | 04.09.2015 | All | The possibility of setting up email escalation for the packed instruction if remains unattended for long time |  |  | Medium
4 | 05.09.2015 | Originator | The possibility of knowing the account segment during uploading instruction. Currently Originators are supposed to know customers off head. |  |  | Low
5 | 05.09.2015 | Payment Processing | Setting up the applicable cut-off times in the systems so that any payment received after cut-off time should not go the processing team and remain at DD stage. TL Payments can have a screen where they can set cut-off time as they wish. |  |  | High
6 | 05.09.2015 | Payments | To have EOD reports for processing teams which will have a column to show all branches since they will receive payments from all branches but the originator should be able to only see for their branch. OTT/RTGS should be separated from Vouchers/Salaries since they are processed with different teams |  | Option to select all branches should be available for Payments team | High
7 | 25.09.2015 | Originator | Originator to be able to edit instruction type when payment is return to them but the reference to indicate Modified and the same be tracked in audit trail. Currently they only delete and reload another instruction due to this restriction. |  |  | Medium
8 | 25.09.2015 | Status | We need to clean-up payment status and remain only with what is applicable |  |  | Low
9 | 25.09.2015 | CCC | Possibility of three users with different profiles. i.e. Payment Originator for CIB, Call-back officer for CIB and PRMO for CIB to have one Team leader this is in particular for teams with teams with few people but their unit is involved in more than one activity |  | Is it possible for DD& Call-back to be done by one person? What will happen to our flow? | Low
10 | 25.09.2015 | CCC | Possibility of CCC users to have all the three profile rights .i.e. Originator, Call-back and PRMO. But the user one user should not be able to perform a task end to end. Egg originate, perform call-back and DD. This is for purpose of backup and the team has few staff but involved in multiple activities i.e. Corporate Client Care. |  | Is it possible for DD& Call-back to be done by one person? What will ha pen to our flow? | Low
11 | 25.09.2017 | Salary | All salaries should have an option submit to PRMO option currently PBB goes to PRMO while CIB goes to Payments team who in turn will have to forward to PRMO. This causes delays in processing |  |  | High
12 | 12.10.2015 | Payments/PRMO | Payments which were returned to branches a day before should always come at the top of the queue when the same is returned to processing team |  |  | Medium
13 |  | RM/Transaction Bankers | Disable all email alert to RMs/Transaction Bankers during normal activities. They currently receive emails for every activity happening on an instruction. RMs should receive emails only when an instruction is returned for a specified reason |  |  | High
14 |  | all | When an instruction is returned to originator an email notification is not sent to them thus making users to write emails notifying them but if the same is recalled an email notification will be generated |  |  | High

## Malawai
Malawi Change Request Document
Document: